## Ghantt Chart
Task | Start Date | End Date | Duration
Define Project Scope and Requirements | 2023-04-11 | 2023-04-18 | 7
Develop Project Plan and Timeline | 2023-04-18 | 2023-04-25 | 7
Define End Goal | 2023-04-18 | 2023-04-19 | 1
Determine Relevent Information to give A.I. | 2023-04-25 | 2023-05-09 | 14
Collect and Process Data | 2023-05-09 | 2024-05-09 | 366
Clean Collected Data | 2024-05-09 | 2024-08-09 | 92
Label Data for Processing | 2024-08-09 | 2024-11-09 | 92
Develop A.I. Model | 2024-11-09 | 2025-03-09 | 120
Select Machine Learning Algorithm | 2024-11-09 | 2024-11-16 | 7
Train Model with Machine Learning Algorithm | 2025-03-09 | 2025-08-09 | 153
Test A.I. for Accuracy | 2025-08-09 | 2026-02-09 | 184
Develop API for A.I. Output | 2026-02-09 | 2026-03-09 | 28
Create Documentation and User Manuals | 2026-02-09 | 2026-02-23 | 14
Release to the Public | 2026-02-23 | 2026-02-24 | 1
0
0
0
0
0
0
0
0
0
0

## Sheet1 (2)
Task | Start Date | End Date | Duration
Define Project Scope and Requirements | 2023-04-11 | 2023-04-18 | 7
Develop Project Plan and Timeline | 2023-04-18 | 2023-04-25 | 7
Define End Goal | 2023-04-18 | 2023-04-19 | 1
Determine Relevent Information to give A.I. | 2023-04-25 | 2023-05-09 | 14
Collect and Process Data | 2023-05-09 | 2024-05-09 | 366
Clean Collected Data | 2024-05-09 | 2024-08-09 | 92
Label Data for Processing | 2024-08-09 | 2024-11-09 | 92
Develop A.I. Model | 2024-11-09 | 2025-03-09 | 120
Select Machine Learning Algorithm | 2024-11-09 | 2024-11-16 | 7
Train Model with Machine Learning Algorithm | 2025-03-09 | 2025-08-09 | 153
Test A.I. for Accuracy | 2025-08-09 | 2026-02-09 | 184
Develop API for A.I. Output | 2026-02-09 | 2026-03-09 | 28
Create Documentation and User Manuals | 2026-02-09 | 2026-02-23 | 14
Release to the Public | 2026-02-23 | 2026-02-24 | 1
0
0
0
0
0
0
0
0
0
0